Summary of TAG/PAG Meeting on 04-04-17

TAG

The goal of the meeting was to finalize the data analysis methods desired by the TAG and to work toward defining appropriate WQ thresholds for each reserve. These goals were not met, but we are getting close.

Since the kick-off meeting there have only been slight changes to the list of desired analyses. In most cases, a few layers of nuance have been added. First, analysis #1 and #2 (annual time series and anomalies for the analysis year) have been merged and modified to include more background context. The new analysis will include the annual time series for the target year and a comparison of that time series to long-term percentiles of averages (see powerpoint slides 7 through 9 for potential examples). Analysis #3 should account for the fact that nutrients are collected on a monthly basis. Analysis #4 has not changed. A final decision on analyses #5 through #7 has not been reached. The TAG is discussing which parameters should be assessed in terms or frequency, duration, and magnitude. Currently, the only consensus is for DO (at 2 mg/L). The TAG is also still discussing an appropriate method for a parameter-specific index score. See the next paragraph for more detail.

The TAG did not approve of WQ thresholds/index scores for all parameters. The TAG is most comfortable establishing thresholds only for certain parameters: DO, chlorophyll-a, and the nutrients with criteria listed in Bricker or the EPA Coastal Conditions Report. Thresholds for turbidity, water temperature, salinity, and pH don’t make sense. Those parameters could instead be compared against long-term percentiles. The TAG also wants the ability to assess trends without assigning a value judgement during the analysis (e.g., our estuary goes anoxic often, but that’s ok for this location).

Additional commentary:

- How much should we emphasize the analysis of the current year vs. the overall picture (trend)? This is a question the TAG wants to make sure the PAG addresses.

Additional questions for TAG to consider:

- Do the planned analyses work across all reserves? If not, is that ok?

Next steps planned:

- Review updated TAG_Analyses_Matrix and approve or correct as needed.

- Discuss the appropriate level of aggregation for each analysis (if different than what LimnoTech specifies in the excel workbook [see action items]).

Decisions reached:

- WQ thresholds are only appropriate for certain parameters, specifically DO, chl-a, and certain nutrients

- Parameters that are not assessed according to a threshold should be assessed based on some percentile comparison or benchmark. The appropriate percentile has not yet been established

Action items:

- LimnoTech will update the TAG_Analyses_Matrix excel workbook with their current understanding of the desired data analyses (on a parameter-by-parameter) basis.

- TAG will work to confirm/clarify/correct the TAG_Analyses_Matrix and finalize type of analysis desired for each parameter.

- TAG will work through remaining questions LimnoTech sent to Dave on 3/17/17 (Dave contact Julie if you would like clarification).

Attendees:

| Full Name | First Name | Last Name | Group | 04/04/17 Attendance |
| --- | --- | --- | --- | --- |
| Denise Sanger | Denise | Sanger | NERRS | X |
| Erik Smith | Erik | Smith | NERRS | X |
| Kari StLaurent | Kari | StLaurent | NERRS | X |
| Kerstin Wasson | Kerstin | Wasson | NERRS | X |
| Kimberly Cressman | Kimberly | Cressman | NERRS | X |
| Kristi Arend | Kristi | Arend | NERRS | X |
| Nikki Dix | Nikki | Dix | NERRS | X |
| Dwight Trueblood | Dwight | Trueblood | NOAA | X |
| Dave Eslinger | Dave | Eslinger | NOAA | X |
| Julie Padilla | Julie | Padilla | LimnoTech | X |
| Tim Dekker | Tim | Dekker | LimnoTech | X |
| Amanda Flynn | Amanda | Flynn | LimnoTech | X |
| Anthony Aufdenkampe | Anthony | Aufdenkampe | LimnoTech | X |

PAG

The goal of this meeting was to define the typical audience for the reserves and to establish key communication goals for the reserves. Both of these goals were met.

The target audience for the status reports is extremely diverse. It may include K-12 teachers, employees of the state environmental agency, staff from the health department, shellfish growers, and recreationists, to name a few. Generally, the audience appears to be general citizens that may have a vested interest in water quality in the reserve.

“How is my estuary doing?” seems to be a good starting point for reserve level reporting. All reserves with water quality ranging from impaired to pristine receive this type of question from visitors. A secondary goal would highlight the benefits that the reserve provides.

Outreach focused staff at some reserves have used other water quality report cards to generate conversation and interaction with the local community. Both Elkhorn Slough and Old Woman Creek have had success engaging their visitors/community using water quality report cards. These report cards focus on assigning letter grades, without too much background context. The end user usually gets the context for the water quality scores from further inquiry.

While some reserves have successfully implemented WQ “report cards”, this method is not likely to be approved by the TAG. Instead, the reports should focus on identifying increasing and decreasing trends. Perhaps these trends could be denoted with either directional arrows or plus/minus signs. This type of analysis could also work well for pristine estuaries that would likely receive all “A” grades.

There was consensus that outreach-focused staff would also be expected to spend some time generating this annual report. The amount of time is unclear, but based on comments during the conversation, the template should require only the minimum amount of customization before it is ready for publication. However, ECs definitely want the ability to get into the final report and edit/reinterpret text to better describe data from their reserve.

Additional commentary:

- An 18 month turn-around time between data collection and reporting is too long. We should look into methods to decrease this time for the needs of the report.

Decisions reached:

- The primary audience is very diverse, but has an interest in water quality. In general, the more simple the plots and graphics the better so that the reports can meet the needs of several audiences.

- The primary communication goal for the report is to answer the question, “how is my estuary doing?” A secondary goal is to communicate the value of the estuaries.

- Both the PAG and the TAG have a common interest in describing longterm trends in SWMP data

Action Items:

- LimnoTech: develop a series of questions for the PAG to work through at their next meeting.

Attendees:

| Full Name | First Name | Last Name | Group | 04/04/17 Attendance |
| --- | --- | --- | --- | --- |
| Bre Hohman | Bre | Hohman | NERRS | X |
| Cathy Angell | Cathy | Angell | NERRS | X |
| Erik Smith | Erik | Smith | NERRS | X |
| Jen Rollins | Jen | Rollins | NERRS | X |
| Joan Muller | Joan | Muller | NERRS | X |
| Kerstin Wasson | Kerstin | Wasson | NERRS | X |
| Mike Shirley | Mike | Shirley | NERRS |  |
| Sarah Ferner | Sarah | Ferner | NERRS | X |
| Nikki Dix | Nikki | Dix | NERRS | X |
| John Bragg | John | Bragg | NERRS |  |
| Dwight Trueblood | Dwight | Trueblood | NOAA | X |
| Dave Eslinger | Dave | Eslinger | NOAA | X |
| Julie Padilla | Julie | Padilla | LimnoTech | X |
| Tim Dekker | Tim | Dekker | LimnoTech | X |
| Amanda Flynn | Amanda | Flynn | LimnoTech | X |
| Anthony Aufdenkampe | Anthony | Aufdenkampe | LimnoTech | X |
| Jen Read | Jen | Read | Univ. of Michigan | X |

Common ground between TAG and PAG:

- The TRENDS are the most important assessment

- A complete reserve-level annual report should have a very low time commitment

- The reserve-level report should also be easily customizable for reserves that do have additional time available

- TAG member who are on the PAG seemed comfortable with a plus/minus trend identification